## 1. Project Overview
PROJECT OVERVIEW
1. Project Description
Project Name |  | Đề thi và chấm thi bằng .NET CORE | Group | FM Nha Trang
Project Code |  | FM_DETHI | Division | Dev
Contract Type |  |  | Project Type | External
Customer |  |  | Project Manager | Mã Phi Hùng
2nd Customer |  |  | Project Category | Development
Project Level |  | Team | Business Domain | Tech
Project Rank |  |  | Application Type | Web Application
2. Scope
No | Items
1 | Build website "De Thi Online" with .NET CORE
- | -
- | -
- | -
3. Out of scope
No | Items
- | -
4. Deliverables
No | Product release |  | Release date | Acceptance criteria
1 | Weekly meeting |  | Every day
2 | Phase 1 (Design system, database, UI/UX, model,...) |  | 3 days after kick-off
3 | Phase 2 (Test case, API Controller Login, Register,view Login, view Register) |  | 5 days after kick-off
4 | Phase 3 (Test case, API Controller Tests, Question ,view Home, view Create Test, view Answer) |  | 6 days after kick-off
5 | Phase 4 (Test case, API Controller History_Answer, view Answer, view History_answer) |  | 7 days after kick-off
6 | Phase 5 (Testing, Report) |  | 8 days after kick-off
7 | Phase 2 (Fix, Complete Website) |  | 9 days after kick-off
9 | Final release |  | 10 days after kick-off
5. Project planning
Creator |  | Mã Phi Hùng | Created Date | 2020-10-01
Reviewer |  |  | Review Date
Approval |  |  | Approve Date
Customer |  |  | Version | 1

## 3.Planing
Plan working
No. | Stage | Days
|  | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20
1 | Bắt đầu dự án
2 | Họp triển khai dự án
2.1 | Xác định sơ lược chức năng của phần mềm
3 | Phân công công việc
4 | Phân tích hệ thống, sơ đồ chức năng, cơ sở dữ liệu
5 | Tìm hiểu sơ lược .NET Core, Angular,…. Cài đặt framework
7 | Tạo cơ sở dữ liệu, project, github,…
8 | Họp xác định nội dung website và bắt đầu code
9 | Tạo document cho dự án
10 | Tạo test case
11 | Design UI/UX
12 | Code API User (Login, Register, Info, Update, Delete,…)
13 | Code view Login, Register
14 | Code API Tests (Add, GetAll, Get, Update, Delete,…)
15 | Code view Home, Menu-bar
16 | Code API Question (Add, Get, Update, Delete,…)
17 | Code view Create Test, History answer
18 | Code API History_Answer (Add, Get, Update, Delete,…)
19 | Code view Answer
20 | Complete source code
21 | Testing, Report
22 | Fix, Complete website
24 | Final project

## 3. Fixbug
Risk/Bug Management

## 4. Report
Quality Management
1. Review Strategy
No | Review Item | Reviewer | Review Type | Review Method | Completion Criteria
2. Test Strategy
Unit Test
No | Item to be Unit Tested | Unit Test Type | Unit Test Technique | Tool Used | Unit Test Completion Criteria
1 |  |  |  |  | <When the testing is ended>
2
3
Integration Test
No | Item to be Integration Tested | Integration Test Type | Integration Test Technique | Tool Used | Unit Test Completion Criteria
1 |  |  |  |  | <When the testing is ended>
2
3
System Test
No | Item to be System Tested | System Test Type | System Test Technique | Tool Used | Completion Criteria
1 |  |  |  |  | <When the testing is ended>
2
3